## Schedule
Outline Level | WBS | Task Name | Parent WBS | Duration | Start | End | Milestone | Dependencies | Source Notes
1 | 1 | Permission to Start |  | 9w | 2026-03-01 | 2026-05-13 | No
2 | 1.1 | Grant Award | 1 |  | 2026-03-01 | 2026-03-01 | Yes |  | Milestone extracted from PDF programme.
2 | 1.2 | Collate documentation | 1 | 7w | 2026-03-01 | 2026-04-30 | No
2 | 1.3 | NLHF Review | 1 | 1w | 2026-05-02 | 2026-05-06 | No
2 | 1.4 | Start up meeting | 1 | 1w | 2026-05-09 | 2026-05-13 | No
2 | 1.5 | PTS gained | 1 |  | 2026-05-13 | 2026-05-13 | Yes |  | Milestone extracted from PDF programme.
1 | 2 | Project Board |  | 47w | 2026-05-16 | 2027-04-08 | No
2 | 2.1 | Project Board Meeting #1 | 2 | 1w | 2026-05-16 | 2026-05-20 | No
2 | 2.2 | Project Board Meeting #2 | 2 | 1w | 2026-08-18 | 2026-08-22 | No
2 | 2.3 | Project Board Meeting #3 | 2 | 1w | 2026-11-17 | 2026-11-21 | No
2 | 2.4 | Project Board Meeting #4 | 2 | 1w | 2027-04-04 | 2027-04-08 | No
1 | 3 | Heritage Fund Reporting |  | 40w | 2026-08-25 | 2027-05-26 | No
2 | 3.1 | Progress Meeting #1 | 3 | 1w | 2026-08-25 | 2026-08-29 | No
2 | 3.2 | Progress Meeting #2 | 3 | 1w | 2026-11-24 | 2026-11-28 | No
2 | 3.3 | Progress Meeting #3 | 3 | 1w | 2027-02-09 | 2027-02-13 | No
2 | 3.4 | Progress Meeting #4 | 3 | 1w | 2027-04-04 | 2027-04-08 | No
2 | 3.5 | Grant Payment Request #2 | 3 | 2w | 2026-11-30 | 2026-12-11 | No
2 | 3.6 | Grant Payment Request #3 | 3 | 2w | 2027-05-15 | 2027-05-26 | No
1 | 4 | Consultant Procurement & Appointment |  | 12w | 2026-04-12 | 2026-07-03 | No
2 | 4.1 | Project Manager (procure at risk) | 4 | 4w | 2026-04-12 | 2026-05-06 | No
2 | 4.2 | Master Planning | 4 | 4w | 2026-05-09 | 2026-06-06 | No
2 | 4.3 | Business Planner | 4 | 4w | 2026-06-09 | 2026-07-03 | No
2 | 4.4 | Governance & Organisational Development | 4 | 4w | 2026-06-09 | 2026-07-03 | No
2 | 4.5 | Fundraising Consultant | 4 | 4w | 2026-06-09 | 2026-07-03 | No
2 | 4.6 | Evaluation Consultant | 4 | 4w | 2026-06-09 | 2026-07-03 | No
1 | 5 | WS1: Vision & Strategy |  | 52w | 2026-05-16 | 2027-05-12 | No
2 | 5.1 | Development of Vision | 5 | 26w | 2026-05-16 | 2026-11-14 | No
2 | 5.2 | Development of Strategy | 5 | 26w | 2026-10-06 | 2027-04-01 | No
2 | 5.3 | Implementation / Action Plan | 5 | 12w | 2027-02-23 | 2027-05-12 | No
1 | 6 | WS2: Community & Stakeholder Engagement |  | 52w | 2026-05-16 | 2027-05-12 | No
2 | 6.1 | Phase 1: Listening & Community Research | 6 | 24w | 2026-05-16 | 2026-10-31 | No
2 | 6.2 | Phase 2: Developing & Refining Proposals | 6 | 24w | 2026-10-06 | 2027-03-18 | No
2 | 6.3 | Phase 3: Validation / Consensus Check | 6 | 12w | 2027-02-23 | 2027-05-12 | No
2 | 6.4 | Community Stakeholder Meeting #1 | 6 | 1w | 2026-06-09 | 2026-06-13 | No
2 | 6.5 | Community Stakeholder Meeting #2 | 6 | 1w | 2026-09-08 | 2026-09-12 | No
2 | 6.6 | Community Stakeholder Meeting #3 | 6 | 1w | 2026-12-07 | 2026-12-11 | No
2 | 6.7 | Community Stakeholder Meeting #4 | 6 | 1w | 2027-04-18 | 2027-04-22 | No
1 | 7 | WS3: Masterplanning |  | 40w | 2026-07-06 | 2027-04-08 | No
2 | 7.1 | Initial review and survey | 7 | 12w | 2026-07-06 | 2026-09-26 | No
2 | 7.2 | Drafting proposals | 7 | 12w | 2026-09-29 | 2026-12-18 | No
2 | 7.3 | Consultation on draft proposals | 7 | 8w | 2026-12-21 | 2027-02-13 | No
2 | 7.4 | Refining proposals | 7 | 4w | 2027-02-16 | 2027-03-11 | No
2 | 7.5 | Reporting | 7 | 4w | 2027-03-14 | 2027-04-08 | No
1 | 8 | WS4: Delivery Model |  | 24w | 2026-12-14 | 2027-05-26 | No
2 | 8.1 | Business Planning | 8 | 24w | 2026-12-14 | 2027-05-26 | No
3 | 8.1.1 | Baselining | 8.1 | 8w | 2026-12-14 | 2027-02-06 | No
3 | 8.1.2 | Developing Options | 8.1 | 8w | 2027-02-09 | 2027-04-01 | No
3 | 8.1.3 | Refining Options | 8.1 | 8w | 2027-04-04 | 2027-05-26 | No
3 | 8.1.4 | BP completed | 8.1 |  | 2027-05-26 | 2027-05-26 | Yes |  | Milestone extracted from PDF programme.
2 | 8.2 | Governance and organisational development | 8 | 20w | 2027-01-12 | 2027-05-26 | No
3 | 8.2.1 | Baselining | 8.2 | 8w | 2027-01-12 | 2027-03-04 | No
3 | 8.2.2 | Developing Proposals | 8.2 | 8w | 2027-03-07 | 2027-04-29 | No
3 | 8.2.3 | Refining Proposals | 8.2 | 4w | 2027-05-01 | 2027-05-26 | No
3 | 8.2.4 | GOD completed | 8.2 |  | 2027-05-26 | 2027-05-26 | Yes |  | Milestone extracted from PDF programme.
2 | 8.3 | Funding Plan and Strategy | 8 | 8w | 2027-04-04 | 2027-05-26 | No
3 | 8.3.1 | Draft options | 8.3 | 4w | 2027-04-04 | 2027-04-29 | No
3 | 8.3.2 | Final options | 8.3 | 4w | 2027-05-01 | 2027-05-26 | No
3 | 8.3.3 | Fundraising Plan completed | 8.3 |  | 2027-05-26 | 2027-05-26 | Yes |  | Milestone extracted from PDF programme.
2 | 8.4 | Delivery Plan | 8 | 8w | 2027-04-04 | 2027-05-26 | No
3 | 8.4.1 | Draft Delivery Plan | 8.4 | 4w | 2027-04-04 | 2027-04-29 | No
3 | 8.4.2 | Final Delivery Plan | 8.4 | 4w | 2027-05-01 | 2027-05-26 | No
3 | 8.4.3 | Delivery Plan completed | 8.4 |  | 2027-05-26 | 2027-05-26 | Yes |  | Milestone extracted from PDF programme.
1 | 9 | WS5: Programme & Project Management |  | 20w 3d | 2027-02-09 | 2027-06-30 | No
2 | 9.1 | Feasibility Study Report | 9 | 16w | 2027-02-09 | 2027-05-26 | No
3 | 9.1.1 | Draft Feasibility Study | 9.1 | 8w | 2027-02-09 | 2027-04-01 | No
3 | 9.1.2 | Consultation on Draft | 9.1 | 4w | 2027-04-04 | 2027-04-29 | No
3 | 9.1.3 | Final Feasibility Study | 9.1 | 4w | 2027-05-01 | 2027-05-26 | No
3 | 9.1.4 | FS completed | 9.1 |  | 2027-05-26 | 2027-05-26 | Yes |  | Milestone extracted from PDF programme.
2 | 9.2 | Project Evaluation | 9 | 20w | 2027-02-12 | 2027-06-30 | No
3 | 9.2.1 | Initial set up | 9.2 | 4w | 2027-02-12 | 2027-03-09 | No
3 | 9.2.2 | Review data / Meetings | 9.2 | 8w | 2027-03-10 | 2027-05-03 | No
3 | 9.2.3 | Draft Evaluation Report | 9.2 | 4w | 2027-05-04 | 2027-06-03 | No
3 | 9.2.4 | Final Evaluation Report | 9.2 | 2w | 2027-06-18 | 2027-06-30 | No
1 | 10 | Project Completion |  |  | 2027-06-30 | 2027-06-30 | Yes |  | Milestone extracted from PDF programme.

## Gantt
Celebration Bournville Feasibility Study Delivery Programme 2026/27
[6 empty] | Feb 2026 | Mar 2026 |  |  |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026 |  |  |  | Oct 2026 |  |  |  | Nov 2026 |  |  |  |  | Dec 2026 |  |  |  | Jan 2027 |  |  |  | Feb 2027 |  |  |  | Mar 2027 |  |  |  |  | Apr 2027 |  |  |  | May 2027 |  |  |  |  | Jun 2027
WBS | Task Name | Duration | Start | End | Milestone | time axis 2026-02-23 to 2027-06-28
1 | Permission to Start | 9w | 2026-03-01 | 2026-05-13
1.1 | Grant Award |  | 2026-03-01 | 2026-03-01 | Yes | bar: 2026-02-23
1.2 | Collate documentation | 7w | 2026-03-01 | 2026-04-30
1.3 | NLHF Review | 1w | 2026-05-02 | 2026-05-06
1.4 | Start up meeting | 1w | 2026-05-09 | 2026-05-13
1.5 | PTS gained |  | 2026-05-13 | 2026-05-13 | Yes | bar: 2026-05-11
2 | Project Board | 47w | 2026-05-16 | 2027-04-08
2.1 | Project Board Meeting #1 | 1w | 2026-05-16 | 2026-05-20
2.2 | Project Board Meeting #2 | 1w | 2026-08-18 | 2026-08-22
2.3 | Project Board Meeting #3 | 1w | 2026-11-17 | 2026-11-21
2.4 | Project Board Meeting #4 | 1w | 2027-04-04 | 2027-04-08
3 | Heritage Fund Reporting | 40w | 2026-08-25 | 2027-05-26
3.1 | Progress Meeting #1 | 1w | 2026-08-25 | 2026-08-29
3.2 | Progress Meeting #2 | 1w | 2026-11-24 | 2026-11-28
3.3 | Progress Meeting #3 | 1w | 2027-02-09 | 2027-02-13
3.4 | Progress Meeting #4 | 1w | 2027-04-04 | 2027-04-08
3.5 | Grant Payment Request #2 | 2w | 2026-11-30 | 2026-12-11
3.6 | Grant Payment Request #3 | 2w | 2027-05-15 | 2027-05-26
4 | Consultant Procurement & Appointment | 12w | 2026-04-12 | 2026-07-03
4.1 | Project Manager (procure at risk) | 4w | 2026-04-12 | 2026-05-06
4.2 | Master Planning | 4w | 2026-05-09 | 2026-06-06
4.3 | Business Planner | 4w | 2026-06-09 | 2026-07-03
4.4 | Governance & Organisational Development | 4w | 2026-06-09 | 2026-07-03
4.5 | Fundraising Consultant | 4w | 2026-06-09 | 2026-07-03
4.6 | Evaluation Consultant | 4w | 2026-06-09 | 2026-07-03
5 | WS1: Vision & Strategy | 52w | 2026-05-16 | 2027-05-12
5.1 | Development of Vision | 26w | 2026-05-16 | 2026-11-14
5.2 | Development of Strategy | 26w | 2026-10-06 | 2027-04-01
5.3 | Implementation / Action Plan | 12w | 2027-02-23 | 2027-05-12
6 | WS2: Community & Stakeholder Engagement | 52w | 2026-05-16 | 2027-05-12
6.1 | Phase 1: Listening & Community Research | 24w | 2026-05-16 | 2026-10-31
6.2 | Phase 2: Developing & Refining Proposals | 24w | 2026-10-06 | 2027-03-18
6.3 | Phase 3: Validation / Consensus Check | 12w | 2027-02-23 | 2027-05-12
6.4 | Community Stakeholder Meeting #1 | 1w | 2026-06-09 | 2026-06-13
6.5 | Community Stakeholder Meeting #2 | 1w | 2026-09-08 | 2026-09-12
6.6 | Community Stakeholder Meeting #3 | 1w | 2026-12-07 | 2026-12-11
6.7 | Community Stakeholder Meeting #4 | 1w | 2027-04-18 | 2027-04-22
7 | WS3: Masterplanning | 40w | 2026-07-06 | 2027-04-08
7.1 | Initial review and survey | 12w | 2026-07-06 | 2026-09-26
7.2 | Drafting proposals | 12w | 2026-09-29 | 2026-12-18
7.3 | Consultation on draft proposals | 8w | 2026-12-21 | 2027-02-13
7.4 | Refining proposals | 4w | 2027-02-16 | 2027-03-11
7.5 | Reporting | 4w | 2027-03-14 | 2027-04-08
8 | WS4: Delivery Model | 24w | 2026-12-14 | 2027-05-26
8.1 | Business Planning | 24w | 2026-12-14 | 2027-05-26
8.1.1 | Baselining | 8w | 2026-12-14 | 2027-02-06
8.1.2 | Developing Options | 8w | 2027-02-09 | 2027-04-01
8.1.3 | Refining Options | 8w | 2027-04-04 | 2027-05-26
8.1.4 | BP completed |  | 2027-05-26 | 2027-05-26 | Yes | bar: 2026-02-23 to 2027-06-28
8.2 | Governance and organisational development | 20w | 2027-01-12 | 2027-05-26
8.2.1 | Baselining | 8w | 2027-01-12 | 2027-03-04
8.2.2 | Developing Proposals | 8w | 2027-03-07 | 2027-04-29
8.2.3 | Refining Proposals | 4w | 2027-05-01 | 2027-05-26
8.2.4 | GOD completed |  | 2027-05-26 | 2027-05-26 | Yes | bar: 2027-05-24
8.3 | Funding Plan and Strategy | 8w | 2027-04-04 | 2027-05-26
8.3.1 | Draft options | 4w | 2027-04-04 | 2027-04-29
8.3.2 | Final options | 4w | 2027-05-01 | 2027-05-26
8.3.3 | Fundraising Plan completed |  | 2027-05-26 | 2027-05-26 | Yes | bar: 2027-05-24
8.4 | Delivery Plan | 8w | 2027-04-04 | 2027-05-26
8.4.1 | Draft Delivery Plan | 4w | 2027-04-04 | 2027-04-29
8.4.2 | Final Delivery Plan | 4w | 2027-05-01 | 2027-05-26
8.4.3 | Delivery Plan completed |  | 2027-05-26 | 2027-05-26 | Yes | bar: 2027-05-24
9 | WS5: Programme & Project Management | 20w 3d | 2027-02-09 | 2027-06-30
9.1 | Feasibility Study Report | 16w | 2027-02-09 | 2027-05-26
9.1.1 | Draft Feasibility Study | 8w | 2027-02-09 | 2027-04-01
9.1.2 | Consultation on Draft | 4w | 2027-04-04 | 2027-04-29
9.1.3 | Final Feasibility Study | 4w | 2027-05-01 | 2027-05-26
9.1.4 | FS completed |  | 2027-05-26 | 2027-05-26 | Yes | bar: 2027-05-24
9.2 | Project Evaluation | 20w | 2027-02-12 | 2027-06-30
9.2.1 | Initial set up | 4w | 2027-02-12 | 2027-03-09
9.2.2 | Review data / Meetings | 8w | 2027-03-10 | 2027-05-03
9.2.3 | Draft Evaluation Report | 4w | 2027-05-04 | 2027-06-03
9.2.4 | Final Evaluation Report | 2w | 2027-06-18 | 2027-06-30
10 | Project Completion |  | 2027-06-30 | 2027-06-30 | Yes | bar: 2027-06-28